## Gantt
Momentum — Roadmap Gantt (V1 Deferred → V4)
Scheduled by dependency within each release deadline. Generated 2026-06-28.
[7 empty] | Jun 2026 | [10 empty] | Jul 2026 | [30 empty] | Aug 2026
ID | Task | Ver | Depends On | Start | End | Days | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
V1.1 | Classification engine (allowed/disallowed, strict mode, real classify()) | V1 | — | 2026-06-20 | 2026-06-22 | 3
V1.2 | 'Feeling distracted' popup trigger + bring-to-front + dynamic copy | V1 | V1.1 | 2026-06-23 | 2026-06-24 | 2
V1.3 | Timer + Windows notification for 10-min log countdown | V1 | — | 2026-06-20 | 2026-06-21 | 2
V1.4 | Settings screen (thresholds, strict mode, name) functioning | V1 | V1.1 | 2026-06-23 | 2026-06-24 | 2
V1.5 | Daily carry-over + weekly list + task-create menu + Calendar | V1 | — | 2026-06-20 | 2026-06-22 | 3
V1.6 | Splash animation (offset-path snowball tuning) | V1 | — | 2026-06-20 | 2026-06-20 | 1
V1.7 | Productivity Trends page (separate from Current Session) | V1 | V1.1 | 2026-06-23 | 2026-06-24 | 2
V1.8 | Verify logs save & can be reviewed | V1 | V1.3 | 2026-06-22 | 2026-06-22 | 1
V1.9 | Reduce clutter / resize cards in log flow | V1 | V1.8 | 2026-06-23 | 2026-06-23 | 1
V1.10 | npm run dev: remove/rename Electron print statements | V1 | — | 2026-06-20 | 2026-06-20 | 1
V1.11 | Remove redundant eyebrow text | V1 | — | 2026-06-20 | 2026-06-20 | 1
V1.12 | Link top-right timer & session cards to correct pages | V1 | V1.7 | 2026-06-25 | 2026-06-25 | 1
V1.13 | Review polling structure & SQLite storage | V1 | — | 2026-06-20 | 2026-06-21 | 2
V1.14 | Verify momentum.exe runs (why Windows-approved) | V1 | — | 2026-06-20 | 2026-06-20 | 1
V1.15 | Verify polling: multi-window/monitor, minimized, Edge split | V1 | V1.13, V1.1 | 2026-06-23 | 2026-06-24 | 2
V1.16 | Resolve npm audit warnings | V1 | — | 2026-06-20 | 2026-06-20 | 1
V1.17 | Delete / rename GitHub branch | V1 | — | 2026-06-20 | 2026-06-20 | 1
V1.18 | Security check + crash / edge-case testing | V1 | V1.2, V1.5, V1.7, V1.9, V1.15 | 2026-06-25 | 2026-06-26 | 2
V1.19 | Add V1.0 note to splash screen | V1 | V1.6 | 2026-06-21 | 2026-06-21 | 1
V2.1 | Pomodoro break notifier (auto-fire, modes, settings) | V2 | V1.1, V1.4 | 2026-06-29 | 2026-06-30 | 2
V2.2 | Current session 'live' card (getLiveStatus IPC) | V2 | V1.1 | 2026-06-29 | 2026-06-29 | 1
V2.3 | Profile / About-me page (replaces risk factors) | V2 | — | 2026-06-29 | 2026-06-30 | 2
V2.4 | Local timezone binding + timezone setting w/ override | V2 | V1.4 | 2026-06-29 | 2026-06-29 | 1
V2.5 | Login popup (welcome, create profile, weekly + daily lists) | V2 | V2.3, V1.5 | 2026-07-01 | 2026-07-02 | 2
V2.6 | Step-breakdown walkthrough popup in task-create | V2 | V1.5 | 2026-06-29 | 2026-06-30 | 2
V2.7 | Drag to reorder tasks / steps | V2 | V1.5 | 2026-06-29 | 2026-06-29 | 1
V2.8 | Verify date/time change reorders daily & calendar views | V2 | V2.7 | 2026-06-30 | 2026-06-30 | 1
V2.9 | Completed work saved to Calendar tab (filters) | V2 | V1.5 | 2026-06-29 | 2026-06-29 | 1
V2.10 | Productivity Trends: full calendar view + more charts | V2 | V1.7 | 2026-06-29 | 2026-06-30 | 2
V2.11 | Add V1.2 note to splash | V2 | V1.19 | 2026-06-29 | 2026-06-29 | 1
V3.1 | Reflection info page (dopamine/avoidance, sourced advice) | V3 | V1.2 | 2026-07-06 | 2026-07-07 | 2
V3.2 | Profile: lock-in / detractor items referenced in popups | V3 | V2.3 | 2026-07-06 | 2026-07-06 | 1
V3.3 | Journal page (thought records, emotions, gratitude) | V3 | — | 2026-07-06 | 2026-07-07 | 2
V3.4 | Claude API integration | V3 | — | 2026-07-06 | 2026-07-08 | 3
V3.5 | Auto step-breakdown via Claude API (first 3 steps) | V3 | V3.4, V2.6 | 2026-07-09 | 2026-07-10 | 2
V3.6 | Goal Tracking page (hours vs computer/phone time, milestones) | V3 | — | 2026-07-06 | 2026-07-07 | 2
V3.7 | Global vs local allowed/disallowed lists per task | V3 | V1.1 | 2026-07-06 | 2026-07-06 | 1
V3.8 | Efficiency stats/trends (started vs completed timestamps) | V3 | V2.10, V1.5 | 2026-07-06 | 2026-07-07 | 2
V3.9 | Task list auto-organized by category (filter buttons) | V3 | V1.5 | 2026-07-06 | 2026-07-06 | 1
V3.10 | Setting: replace log popups with info/stat popup | V3 | V1.4, V1.2 | 2026-07-06 | 2026-07-06 | 1
V4.1 | Mac release + cross-browser (Safari/Chrome/Firefox) | V4 | — | 2026-07-13 | 2026-07-17 | 5
V4.2 | Smart App Control code signing + Win/Mac packaging | V4 | — | 2026-07-13 | 2026-07-16 | 4
V4.3 | 'Help me get started' button for tasks | V4 | V3.5 | 2026-07-13 | 2026-07-14 | 2
V4.4 | Pull sleep data from Garmin | V4 | — | 2026-07-13 | 2026-07-15 | 3
V4.5 | Pull screentime data from iPhone | V4 | — | 2026-07-13 | 2026-07-15 | 3
V4.6 | Personalized popups (Claude + risk/sleep/goal/phone data) | V4 | V3.4, V4.4, V4.5, V3.6 | 2026-07-16 | 2026-07-19 | 4
V4.7 | End of day/week debrief (post-Claude) | V4 | V3.4 | 2026-07-13 | 2026-07-15 | 3
V4.8 | Framer Motion animations | V4 | — | 2026-07-13 | 2026-07-15 | 3
V4.9 | App usage data: streak, total/consecutive days, monthly | V4 | — | 2026-07-13 | 2026-07-14 | 2
V4.10 | Task list auto-populate from Claude email scan | V4 | V3.4, V1.5 | 2026-07-13 | 2026-07-15 | 3
V4.11 | Deadlines feature: Claude auto-populates milestones | V4 | V3.4, V1.5, V3.6 | 2026-07-13 | 2026-07-15 | 3
V4.12 | App licensing / patents for monetization & IP | V4 | — | 2026-07-13 | 2026-07-14 | 2
Legend:
V1 Deferred — due Jun 28
V2 — due Jul 5
V3 — due Jul 12
V4 — due Aug 9
Release deadline
Weekend